## Risk Register
Risk ID | Risk Title | Risk Description | Likelihood (1–5) | Impact (1–5) | Risk Score (L × I) | Risk Rating | Recommended Mitigation | Owner | Status
R-001 | Unauthorized Access to Sensitive Data | Employees may access data beyond their job role due to lack of role-based access controls, increasing the risk of insider threat or accidental disclosure. | 4 | 5 | 20 | Critical | Implement RBAC; conduct quarterly access reviews; enforce least-privilege principle. | IT Security Team | Open
R-002 | Phishing / Social Engineering Attack | Staff may be targeted by phishing emails, leading to credential theft or malware installation due to insufficient security awareness training. | 4 | 4 | 16 | Critical | Deploy annual phishing simulations; mandatory security awareness training; enable MFA on all accounts. | HR / IT Security | In Progress
R-003 | Unpatched Software Vulnerabilities | Systems running outdated software may contain known vulnerabilities exploitable by threat actors, leading to system compromise. | 3 | 5 | 15 | High | Establish a monthly patch management cycle; prioritize Critical/High CVEs within 30 days. | IT Operations | Open
R-004 | Inadequate Data Backup & Recovery | Absence of tested backup procedures may result in permanent data loss following a ransomware attack, hardware failure, or accidental deletion. | 2 | 5 | 10 | High | Implement 3-2-1 backup strategy; test restoration quarterly; document RTO/RPO targets. | IT Operations | Open
R-005 | No Formal Incident Response Plan | Without a documented IRP, the organization may respond inconsistently to security incidents, prolonging recovery time and increasing regulatory exposure. | 3 | 4 | 12 | High | Develop and approve an IRP; assign incident response roles; conduct annual tabletop exercise. | CISO / IT Security | Open
R-006 | Third-Party Vendor Risk | Vendors with access to organizational systems or data may not maintain equivalent security controls, creating a supply chain risk. | 3 | 4 | 12 | High | Implement vendor risk assessment program; require security questionnaires prior to onboarding. | Procurement / IT | Open
R-007 | Weak Password Policy Enforcement | Users may set weak or reused passwords if no technical controls enforce complexity, length, and rotation requirements. | 3 | 3 | 9 | Medium | Enforce password policy via Active Directory; require minimum 12-character passwords; deploy SSO. | IT Security Team | In Progress
R-008 | Lack of Employee Security Training | Staff without regular security training may unknowingly engage in risky behaviors such as using personal devices for work or sharing credentials. | 3 | 3 | 9 | Medium | Roll out annual mandatory security awareness training; track completion rates. | HR | Open
R-009 | Unencrypted Data in Transit | Sensitive data transmitted without encryption may be intercepted via man-in-the-middle attacks, violating confidentiality requirements. | 2 | 4 | 8 | Medium | Enforce TLS 1.2+ on all web services; disable legacy protocols; conduct periodic network scans. | IT Operations | In Progress
R-010 | Physical Security of IT Assets | Unauthorized physical access to server rooms or workstations may allow data theft or hardware tampering. | 2 | 3 | 6 | Low | Implement badge access controls; maintain a visitor log; conduct physical security audits annually. | Facilities / IT | Open

## Risk Summary
Risk Summary Dashboard — TechBridge Solutions
Risk Rating | Count | % of Total
Critical | 2
High | 4
Medium | 3
Low | 1
TOTAL

## Remediation Tracker
Risk ID | Risk Title | Remediation Action | Owner | Target Date | Completion Date | Status
R-001 | Unauthorized Access | Implement RBAC; conduct access reviews | IT Security Team | 2026-08-01 |  | Open
R-002 | Phishing Attack | Deploy phishing simulation + MFA rollout | HR / IT Security | 2026-07-15 |  | In Progress
R-003 | Unpatched Software | Establish monthly patch management cycle | IT Operations | 2026-08-15 |  | Open
R-004 | Data Backup | Implement 3-2-1 backup; test restoration | IT Operations | 2026-09-01 |  | Open
R-005 | No IRP | Draft IRP; assign roles; tabletop exercise | CISO | 2026-09-15 |  | Open
R-006 | Vendor Risk | Deploy vendor risk questionnaire program | Procurement | 2026-10-01 |  | Open
R-007 | Weak Passwords | Enforce AD password policy; deploy SSO | IT Security Team | 2026-07-30 |  | In Progress
R-008 | Security Training | Launch annual awareness training program | HR | 2026-08-30 |  | Open
R-009 | Unencrypted Transit | Enforce TLS 1.2+; disable legacy protocols | IT Operations | 2026-08-01 |  | In Progress
R-010 | Physical Security | Badge access audit; visitor log implementation | Facilities | 2026-12-01 |  | Open